## Logistics
Logistics Meeting ID | Interview #1
Meeting Type | (e.g., Kickoff, Review, Follow-Up, Risk Deep Dive)
Date | 2025-05-01
Start Time | 1PM
End Time | 5PM
Time Zone
Location
Link/URL/Phone
Meeting Format | Video (Zoom), In-person, Hybrid
Meeting Status
Key Notes
Additional Notes | Vendor representative joined last 30 minutes only.
Typical Agenda
Duration | Agenda Item | Start Time | End Time
15 | Introductions & Objectives — Align on scope, roles, and expectations | 13:00 | 13:15
95 | Business & System Overview — Deep dive into business goals, architecture, data flows, and constraints | 13:15 | 14:50
10 | Break | 14:50 | 15:00
35 | Review Key Assumptions (A- Records) — Validate or adjust foundational assumptions | 15:00 | 15:35
50 | Discuss Risks (R-, AR- Records) — Prioritize, clarify, or identify new risks | 15:35 | 16:25
25 | Open Questions & Gaps — Raise any unknowns or deferred discussions | 16:25 | 16:50
10 | Wrap-Up & Next Steps — Confirm actions, decisions, and scheduling | 16:50 | 17:00

## Info Sources
Interview Attendees
Attendees Code | Name | Role/Department | Title | Employer | Email | Phone | Via
SPG | Steve Gibbons | Interviewer/Assessor |  |  |  |  | In Person
AS1 | Allan Stoxton | Facilitator |  |  |  |  | In Person
AS2 | Alex Smith | [5 empty] | Zoom
JD | Jamie Doe | [5 empty] | Telephone
ML | Morgan Lee | Guest/Observer |  |  |  |  | In Person
Referenced Stakeholders
Person Code | Name | Role/Department | Title | Employer | Email | Phone | Via
BB | Bob Bossman | CEO |  |  |  |  | Org Chart
VP | Victor Petrocius | Vice President |  |  |  |  | Org Chart
Referenced Documents
Document Code | Document/Artifact/Resource | ​ | Provided Artifact or Link (or N/A) | Version Evaluated | Also Known As | ​ ​ ​ | Rarity
SAD | System architecture diagrams |  |  |  | HLD, ARCH, AAD |  | 🟢 Common
DFD | Data flow diagrams |  |  |  | DAFD, LPD |  | 🟡 Uncommon
CMDB | Component inventory |  |  |  | SBOM, COMP, CAT |  | 🟡 Uncommon
IAM | AuthN/AuthZ models |  |  |  | SSO, RBAC, OIDC, ABAC, AAA |  | 🟡 Uncommon
DCM | Data classification maps |  |  |  | CLS, DC, INFOSEC TAGS, DL |  | 🔴 Rare
API | External integration descriptions |  |  |  | EXT, EDI, 3PI, IFD |  | 🟡 Uncommon
INF | Hosting & network topology |  |  |  | NTD, NT, NDA, VISIO |  | 🟢 Common
SIEM | Logging & monitoring overview |  |  |  | SOC, LM, MON, LOGS |  | 🟢 Common
CTRL | Security safeguards already implemented |  |  |  | SAFE, CIS, HSC |  | 🟢 Common
SOC2 | Compliance findings (SOC 2, ISO, HIPAA, etc.) |  |  |  | ISO, RPT, AUDIT, GAP |  | 🟢 Common (if regulated)
MBG | Mission or business goal statement |  |  |  | OKR, MBO, VPB |  | 🟢 Common
URS | System purpose / use case overview |  |  |  | BRD, FRD, BRS, EPIC |  | 🟢 Common
STAKE | High-level stakeholder map |  |  |  | RACI, ORG, SMAP |  | 🟡 Uncommon
BIA | Operational criticality tiering |  |  |  | TIER, IMP, DRT, RTO, RPO |  | 🔴 Rare
RTA | Risk tolerance or appetite |  |  |  | KRI, RA, RTM |  | 🔴 Rare
GRC | Regulatory or legal constraints |  |  |  | CC, REQ, LRC |  | 🟢 Common
DEP | Dependencies on other systems |  |  |  | SIPOC, INT, IDM, ICD |  | 🟡 Uncommon
TXP | Expected use patterns |  |  |  | UAM, UCS, UPM |  | 🟢 Common
KAA | Known architectural assumptions |  |  |  | ASSUMP, ARCH NOTE, KBA |  | 🟡 Uncommon
VAPT | Previous risk assessments or pen tests |  |  |  | PT, RSK, RA, SCAN |  | 🟡 Uncommon
ITR | Change plans / roadmaps |  |  |  | RDMP, ITMP, SDLC, MTP |  | 🟡 Uncommon
SLA | SLAs or shared responsibility models |  |  |  | OLA, CSA, SRM, RACI |  | 🟡 Uncommon
DD | M&A diligence summaries |  |  |  | TSA, M&A, ACQ, TRANS |  | 🔴 Rare

## Unified Tracking
|  |  |  | Risk: |  |  |  | Remediation: |  |  |  |  | Resolve:
Record ID | Information Source | Reference Detail (pg#, etc.) | Summary and Details | Risk Context & Impact Domain | Severity¦ Impact | Likelihood¦ Frequency | Inherent Risk | Treatment | Cost | Timeline | Difficulty | Impact (Effectiveness) | Residual Risk | Assigned Owner | Due Date | Status
A-001 |  |  | This model focuses on the onboard software of the Autonomous Driving Stack (ADS), including interactions with sensors, ECUs, and supporting cloud services. | Contextual | Medium | High | High |  |  |  |  | Very Ineffective | High |  |  | Confirm
A-002 |  |  | External systems—such as mobile apps, cloud control planes, and onboard hardware (e.g., powertrain, infotainment)—are out of scope for this phase and will be addressed in future modeling. | Contextual | Low | Low | Minimal | [8 empty] | Open
A-003 |  |  | The system is in a late-stage development phase: most architectural decisions are complete, but refinements may still occur before deployment. | Contextual | [11 empty] | Open
A-004 |  |  | A safety champion with defined authority is responsible for final release decisions, reinforcing safety across the development lifecycle. | Regulatory / Legal Exposure | [11 empty] | Open
A-005 |  |  | Stakeholders—including legal, certification, usability, and marketing—are actively engaged throughout design and release, each holding veto power over go-to-market decisions. | Regulatory / Legal Exposure | [11 empty] | Open
A-006 |  |  | Third-party components must go through formal supplier relationships and require dual signoff by a TMC liaison and supplier release owner before deployment. | Supply Chain / Vendor Impact | [11 empty] | Open
A-007 |  |  | The product owner aligns technical direction with competitive benchmarks and customer value, holding final accountability for release. | Innovation / Product Roadmap | [11 empty] | Open
A-008 |  |  | Threats are modeled against both sophisticated actors (with access to internal knowledge and tools) and less-skilled attackers using commodity exploits. | Contextual | [11 empty] | Open
A-009 |  |  | Attackers are assumed capable of intercepting traffic, accessing physical ports (for at least 30 seconds), and operating compact hardware such as Flipper Zero, smartphones, or Raspberry Pi. | Contextual | [11 empty] | Open
A-010 |  |  | Over-the-air (OTA) updates must be cryptographically signed with hardware-rooted keys, occur only during idle periods, and support rollback to validated versions. | Data Integrity / Quality | [11 empty] | Open
A-011 |  |  | In-cabin design includes voice commands with authentication, no cameras for privacy reasons, and guest Wi-Fi isolated from critical systems with manual console approval required. | Customer Safety / Human Harm | [11 empty] | Open
A-012 |  |  | Attackers are expected to use compact hardware tools (e.g., Flipper Zero, ESP32) to interfere with vehicle components or signals. | Contextual | [11 empty] | Open
A-013 |  |  | Private and sensitive data includes payment credentials, GPS history, personalization settings, and voice input. | Privacy / PII / PHI | [11 empty] | Open
A-014 |  |  | The first and last 100 meters of each trip are considered sensitive due to potential location inference (e.g., home/work). | Privacy / PII / PHI | [11 empty] | Open
A-015 |  |  | Infrastructure data (e.g., maps, traffic feeds) can become sensitive when tied to user-specific queries or patterns. | Privacy / PII / PHI | [11 empty] | Open
A-016 |  |  | Logs and configuration files are privacy-sensitive and must be tamper-resistant and access-controlled. | Privacy / PII / PHI | [11 empty] | Open
A-017 |  |  | Cross-system tokenization and pseudonymization are required to reduce the risk of behavioral re-identification. | Privacy / PII / PHI | [11 empty] | Open
A-018 |  |  | Voice command data is opt-in and user-controllable, including review and deletion via in-app settings. | Privacy / PII / PHI | [11 empty] | Open
A-019 |  |  | All bystander or third-party personal data captured by sensors must be redacted before cloud processing or storage. | Privacy / PII / PHI | [11 empty] | Open
A-020 |  |  | The vehicle operates in urban and metro areas, with optional highway capability available via upgraded trim packages. | Customer Safety / Human Harm | [11 empty] | Open
A-021 |  |  | The vehicle is fully autonomous and lacks manual controls; the user is assumed to be the owner or lessee. | Contextual | [11 empty] | Open
A-022 |  |  | The system incorporates a secure enclave, containerization, full-disk encryption, and hardened third-party software controls. | Privacy / PII / PHI | [11 empty] | Open
A-023 |  |  | OTA updates must be cryptographically signed, occur only when idle, and allow rollback to trusted software versions. | Data Integrity / Quality | [11 empty] | Open
A-024 |  |  | Internal communication may bypass encryption for performance, but only with formal documentation and approval. | Contextual | [11 empty] | Open
A-025 |  |  | All external interfaces (Wi-Fi, cellular, Bluetooth, NFC) are encrypted, authenticated, and monitored by firewalls and IDS. | Privacy / PII / PHI | [11 empty] | Open
A-026 |  |  | Log buffers are circular to avoid exhaustion, with alerting enabled for overwrite events. | Data Integrity / Quality | [11 empty] | Open
A-027 |  |  | Post-quantum cryptography readiness is assumed, with support for agile key rotation. | Privacy / PII / PHI | [11 empty] | Open
A-028 |  |  | In-cabin features exclude cameras, include voice authentication, and isolate guest Wi-Fi from critical systems. | Privacy / PII / PHI | [11 empty] | Open
A-029 |  |  | Sensor data may be used to train ML models only with explicit user consent. | Privacy / PII / PHI | [11 empty] | Open
A-030 |  |  | Rolling cryptographic tokens are used for authenticating ADS control messages to ensure message freshness. | Privacy / PII / PHI | [11 empty] | Open
A-031 |  |  | Real-time congestion data is pulled from secure, trusted, and public infrastructure sources during routing. | Contextual | [11 empty] | Open
A-032 |  |  | Periodic red team assessments are assumed to validate update and communication pathway resilience. | Contextual | [11 empty] | Open
AR-001 |  |  | OTA updates must be cryptographically signed, occur only when idle, and allow rollback to trusted versions. | Customer Safety / Human Harm | High | Medium | High |  |  |  |  | Very Effective | Minimal |  |  | Open
AR-002 |  |  | The secure enclave handles key storage, cryptographic operations, and credential management. | Privacy / PII / PHI | Medium | Low | Low |  |  |  |  | Moderately Effective | Minimal |  |  | Open
AR-003 |  |  | All external interfaces (Wi-Fi, LTE, Bluetooth, NFC) are encrypted, authenticated, and protected by firewalls and intrusion detection. | Privacy / PII / PHI | Medium | Medium | Medium |  |  |  |  | Moderately Effective | Low |  |  | Open
AR-004 |  |  | All third-party or bystander personal data captured must be redacted before cloud transmission or processing. | Customer Safety / Human Harm | High | Low | Medium |  |  |  |  | Very Effective | Minimal |  |  | Open
AR-005 |  |  | The first and last 100 meters of a trip are sensitive due to potential inferences about home/work locations. | Privacy / PII / PHI | Medium | Medium | Medium |  |  |  |  | Moderately Effective | Low |  |  | Open
AR-006 |  |  | The vehicle is fully autonomous with no fallback manual controls; users are assumed to be owners or lessees. | Contextual | Medium | Low | Low |  |  |  |  | Moderately Effective | Minimal |  |  | Open
AR-007 |  |  | Post-quantum cryptographic readiness is assumed, with support for agile key rotation. | Privacy / PII / PHI | High | Medium | High |  |  |  |  | Very Effective | Minimal |  |  | Open
AR-008 |  |  | Log buffers are circular and tamper-evident, with alerts for overwrite events. | Privacy / PII / PHI | Medium | Low | Low |  |  |  |  | Very Effective | Minimal |  |  | Open
I-001 |  |  | Rolling cryptographic tokens are used to authenticate ADS control messages, ensuring freshness and integrity. | Privacy / PII / PHI | [11 empty] | In Progress
I-002 |  |  | Internal vehicle networks are segmented to isolate control traffic and limit message flooding. | Internal Misuse / Insider Threat | [11 empty] | In Progress
I-003 |  |  | Bystander PII is redacted on-device before any media is stored or transmitted. | Privacy / PII / PHI | [11 empty] | In Progress
I-004 |  |  | Intrusion detection systems have been deployed on the in-vehicle network to identify abnormal activity. | Contextual | [11 empty] | In Progress
I-005 |  |  | The organization conducts periodic red team assessments to validate OTA and V2X security resilience. | Contextual | [11 empty] | In Progress
I-006 |  |  | Telemetry data uses tokenized identifiers to reduce the risk of user re-identification. | Privacy / PII / PHI | [11 empty] | In Progress
R-001 |  |  | An attacker injects fake signals to trick ADS into wrong decisions. | Customer Safety / Human Harm | High | Medium | High |  |  |  |  | Very Effective | Minimal |  |  | In Progress
R-002 |  |  | Legitimate sensor data is intercepted or altered, corrupting perception. | Data Integrity / Quality | Medium | Low | Low |  |  |  |  | Moderately Effective | Minimal |  |  | In Progress
R-003 |  |  | Attacker impersonates ADS to issue unauthorized commands. | Unauthorized Access / Misuse | Medium | Medium | Medium |  |  |  |  | Moderately Effective | Low |  |  | In Progress
R-004 |  |  | MITM alters commands in transit (e.g., Brake → Accelerate). | Customer Safety / Human Harm | High | Low | Medium |  |  |  |  | Very Effective | Minimal |  |  | In Progress
R-005 |  |  | Flooding internal network delays or blocks control messages. | Internal Misuse / Insider Threat | Medium | Medium | Medium |  |  |  |  | Moderately Effective | Low |  |  | In Progress
R-006 |  |  | False GPS signals shift vehicle’s perceived location. | Privacy / PII / PHI | Medium | Low | Low |  |  |  |  | Moderately Effective | Minimal |  |  | In Progress
R-007 |  |  | Spoofed road sign or light signals mislead vehicle. | Customer Safety / Human Harm | High | Medium | High |  |  |  |  | Very Effective | Minimal |  |  | In Progress
R-008 |  |  | Manipulated data causes unsafe or illegal routing. | Regulatory / Legal Exposure | Medium | Low | Low |  |  |  |  | Very Effective | Minimal |  |  | In Progress
R-009 |  |  | Unpatched library leads to system compromise. | Customer Safety / Human Harm | Medium | Medium | Medium |  |  |  |  | Moderately Effective | Low |  |  | In Progress
R-010 |  |  | Malformed input can crash the ADS during operation, potentially impacting trip continuity or safety. | Customer Safety / Human Harm | High | Low | Medium |  |  |  |  | Very Effective | Minimal |  |  | In Progress
R-011 |  |  | External datasets can be correlated with driving behavior, potentially re-identifying users. | Privacy / PII / PHI | Medium | Medium | Medium |  |  |  |  | Moderately Effective | Low |  |  | In Progress
R-012 |  |  | Eavesdropping or leaked metadata can allow adversaries to infer or identify the user. | Privacy / PII / PHI | Medium | Low | Low |  |  |  |  | Moderately Effective | Minimal |  |  | In Progress
R-013 |  |  | User actions may be unfairly inferred from logs, resulting in potential misattribution or liability. | Privacy / PII / PHI | High | Medium | High |  |  |  |  | Very Effective | Minimal |  |  | In Progress
R-014 |  |  | Sensor signals may reveal presence or behavior patterns of the user. | Privacy / PII / PHI | Medium | Low | Low |  |  |  |  | Moderately Effective | Minimal |  |  | In Progress
R-015 |  |  | Sensors capture PII (e.g., bystanders). | Privacy / PII / PHI | Medium | Medium | Medium |  |  |  |  | Moderately Effective | Low |  |  | In Progress
R-016 |  |  | Behavior may be inferred from ambient audio and video captured by sensor systems. | Privacy / PII / PHI | High | Low | Medium |  |  |  |  | Very Effective | Minimal |  |  | In Progress
R-017 |  |  | Lack of data governance may violate privacy regulations like GDPR or CCPA. | Regulatory / Legal Exposure | Medium | Medium | Medium |  |  |  |  | Moderately Effective | Low |  |  | In Progress
R-018 |  |  | Driving behavior may be correlated with payment activity, revealing sensitive linkages. | Privacy / PII / PHI | Medium | Low | Low |  |  |  |  | Moderately Effective | Minimal |  |  | In Progress
R-019 |  |  | Route planning data may expose private schedules or routines. | Privacy / PII / PHI | High | Medium | High |  |  |  |  | Very Effective | Minimal |  |  | In Progress
R-020 |  |  | Audio inputs retained or reused without control may breach user privacy expectations. | Privacy / PII / PHI | Medium | Low | Low |  |  |  |  | Moderately Effective | Minimal |  |  | In Progress

## Tables
Severity / Likelihood | Low | Medium | High |  |  | Source Validator | Assignee Validator
Low | Minimal | Low | Medium |  |  | SPG | SPG
Medium | Low | Medium | High |  |  | AS1 | AS1
High | Medium | High | Critical |  |  | AS2 | AS2
Critical | High | Critical | Showstopper |  |  | JD | JD
[6 empty] | ML | ML
Category | Level | Description | Response Guidance | Default Treatment Timeframe |  | BB | BB
Minimal | 0 | No meaningful risk or impact. Observations or notes that require no action but are logged for awareness or traceability. | Log only; no action required | None |  | VP | VP
Low | 1 | Minimal impact and low likelihood. Minor issues that are unlikely to cause harm. May be addressed during routine processes. | Accept or defer; track optionally | Next review cycle (e.g., quarterly) |  | 0 | 0
Medium | 2 | Moderate impact or likelihood. Could cause inefficiencies, non-critical failures, or minor compliance issues. | Mitigate or monitor | Within 30–90 days |  | 0 | 0
High | 3 | Significant impact or likelihood. May result in data exposure, downtime, or reputational harm. | Prompt mitigation required | Within 30 days |  | SAD
Critical | 4 | Severe risk with high likelihood or impact. Could result in legal violations, major outages, or serious financial harm. | Immediate remediation or escalation | Within 7 days |  | DFD
Showstopper | 5 | Unacceptable and systemic risk. Immediate danger to operations, safety, or compliance. | Executive intervention required | Immediate (24–48 hours max) |  | CMDB
IAM
Status | Meaning |  | Difficulty | Description |  | DCM
Confirm | Needs follow-up validation. |  | Very Easy | The task or safeguard can be implemented quickly with minimal effort, skills, or coordination. No significant barriers. |  | API
Open | Identified and active. |  | Easy | Straightforward to implement with common tools or practices. Minor planning or effort required. |  | INF
Not Started | Assigned, but not yet started |  | Moderate | Requires moderate planning, coordination, or expertise. Some dependencies or risks may need to be managed. |  | SIEM
In Progress | Being addressed. |  | Hard | Implementation is complex or resource-intensive. Significant effort, cross-functional support, or |  | CTRL
Closed | Fully resolved. |  | Very Hard | Extremely challenging due to technical, organizational, or cultural constraints. May require major investments or strategic change. |  | SOC2
Deferred | Intentionally delayed. |  |  |  |  | MBG
Blocked | Unable to proceed |  |  |  |  | URS
Promoted to Risk | Escalated into formal risk finding. |  | Effectiveness | Description |  | STAKE
|  |  | Very Ineffective | Controls are either absent, unimplemented, or demonstrably failing. No meaningful reduction in risk. |  | BIA
|  |  | Ineffective | Controls are present but weak, misaligned, or inconsistently applied. Risk is only slightly reduced. |  | RTA
Attended Via |  |  | Moderately Effective | Controls are partially effective. They reduce some aspects of the risk, but gaps remain. |  | GRC
In Person |  |  | Effective | Controls are well-designed, implemented, and actively managed. They significantly reduce the risk. |  | DEP
Telephone |  |  | Very Effective | Controls are mature, proactive, and resilient. Residual risk is minimal and well within tolerance. |  | TXP
Video | [5 empty] | KAA
Did not Attends | [5 empty] | VAPT
ITR
RCID (Previously BIA) | Description |  | Treatment Strategy | Description |  | SLA
Customer Safety / Human Harm | Risks that could result in physical harm, injury, or health consequences to customers or users. |  | Avoid | Eliminate the source of the risk entirely (e.g., remove the feature, cancel the project). |  | DD
Privacy / PII / PHI | Exposure or misuse of personal or health-related data, including violations of privacy regulations. |  | Mitigate (Reduce Likelihood) | Apply controls to lower the chance of occurrence (e.g., hardening, access controls).
Financial Loss | Direct monetary loss to the organization, customers, or partners (fraud, theft, fines, etc.). |  | Mitigate (Reduce Impact) | Reduce the consequences if the risk occurs (e.g., failover, backups).
Reputation / Trust | Damage to brand, customer confidence, or public image. |  | Mitigate (Partial + Accept Residual) | Address what’s feasible, formally accept the remaining residual risk.
Regulatory / Legal Exposure | Violations of laws, regulations, or contractual obligations, including audit failure. |  | Accept | Acknowledge the risk and take no immediate action (e.g., low-priority, business-justified).
Service Continuity / Availability | Disruption or degradation of services, uptime, or business operations. |  | Transfer (Insurance) | Use cyber insurance or similar financial instruments to offset potential losses.
Data Integrity / Quality | Corruption, tampering, or loss of trust in data accuracy or authenticity. |  | Transfer (Contractual) | Shift responsibility to another party through SLAs or third-party agreements.
Unauthorized Access / Misuse | Abuse of privileges, access beyond intended roles, or bypassing intended controls. |  | Monitor Only | Track the risk with no current action planned, often due to uncertainty or emerging nature.
Internal Misuse / Insider Threat | Risk of malicious or accidental actions by employees or internal actors. |  | Escalate | Forward the risk to governance or leadership for review, funding, or executive decision.
Supply Chain / Vendor Impact | Third-party or partner-related risks affecting service, integrity, or compliance. |  | Defer | Temporarily delay treatment, pending redesign or further analysis.
Innovation / Product Roadmap | Risks to future features, technology adoption, or delivery cadence. |  | Retire | Risk no longer applies (e.g., system decommissioned or dependency removed).
Strategic or Mission Disruption | Risks that derail long-term goals, market position, or organizational priorities.
Contextual | Establishes scope or operational assumptions (not a direct impact)
Unclassified | Not yet analyzed
Risk Category / Remediation | Very Ineffective | Ineffective | Moderately Effective | Effective | Very Effective
Minimal | Minimal | Minimal | Minimal | Minimal | Minimal
Low | Low | Low | Minimal | Minimal | Minimal
Medium | Medium | Medium | Low | Minimal | Minimal
High | High | High | Medium | Low | Minimal
Critical | Critical | Critical | High | Medium | Low
Showstopper | Showstopper | Showstopper | Critical | High | Medium