## Sheet1
Record ID | Summary and Details | Category | Severity | Likelihood | To Repair: Cost | To Repair: Timeline | To Repair: Difficulty | Residual Risk | Assigned Owner | Due Date | Status
O-001 | API gateway is hosted internally behind the perimeter firewall. Confirmed verbally by architect during session. | Optional | N/A | N/A | N/A | N/A | N/A | N/A | Optional | Optional | Confirm
A-001 | Assumed idle user sessions expire after 30 mins for compliance. Confirm timeout settings post-deployment. | Optional | N/A | N/A | N/A | N/A | N/A | N/A | Optional | Optional | Confirm
R-001 | Admin interface lacks MFA, increasing compromise risk. Prioritize next sprint. | InfoSec | Critical | High | Low | 1 week | Low | Low | Security Engineer | 2025-05-10 | Open
AI-001 | Confirm if AI chat logs retained or purged. Blocks privacy assessment. | Privacy | N/A | N/A | N/A | N/A | N/A | N/A | Privacy Officer | 2025-05-15 | In Progress
TD-001 | Update architecture diagram to show AI chat integration. Documentation update. | Optional | N/A | N/A | N/A | N/A | N/A | N/A | Lead Architect | 2025-05-20 | Open